## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
I catch CoViD | 3 | 40 | 120 | 2021-01-14 | Mitigated | M | learned instructor has extension possible
My STM32 is not working | 20 | 20 | 400 | 2021-01-14 |  | O | Test it. If mine not working, contact instructor
Wrong drone behavior | 70 | 70 | 4900 |  |  | R
Maze and hole creation issue | 20 | 70 | 1400 |  |  | R
LCD Display issue | 5 | 100 | 500 |  |  | R
Button interrupt not working | 3 | 20 | 60 |  |  | R
Gyro setup issue | 20 | 13 | 260 |  |  | R
0
Week 4: added: |  |  | 0
marble physics behaving weird | 40 | 20 | 800 | 2024-04-17 |  | R | More testing to make sure it works
Energy not working prroperly | 20 | 13 | 260 |  |  | R

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100